Levelling Up Fund Application Form
This form is for bidding entities, applying for funding from the Levelling Up Fund (LUF) across the UK. Prior to completing the application form, applicants should read the LUF Technical Note.
The Levelling Up Fund Prospectus is available here.
The level of detail you provide in the Application Form should be in proportion to the amount of funding that you are requesting. For example, bids for more than £10m should provide considerably more information than bids for less than £10m.
Specifically, for larger transport projects requesting between £20m and £50m, bidding entities may submit the Application Form or if available an Outline Business Case (OBC) or Full Business Case (FBC). Further detail on requirements for larger transport projects is provided in the Technical Note.
One application form should be completed per bid.
Applicant & Bid Information
Local authority name / Applicant name(s)*: Falkirk Council
*If the bid is a joint bid, please enter the names of all participating local authorities / organisations and specify the lead authority
Bid Manager Name and position: Colin Frame, Principal Surveyor, Growth & Investment Unit
Name and position of officer with day-today responsibility for delivering the proposed scheme.
Contact telephone number: 01324 590972 Email address: colin.frame@falkirk.gov.uk
Postal address:	The Falkirk Stadium, Suite 2B, 4 Stadium Way, Falkirk
FK2 9EE
Nominated Local Authority Single Point of Contact: Colin Frame
Senior Responsible Officer contact details: Douglas S. Duff, Head of Planning & Economic Development, Development Services, Falkirk Council, Abbotsford House, David's Loan, Falkirk, FK2 7YZ, Tel. 01324 504952, Mobile: 07738 143626, Fax. 01324 590913, email: douglas.duff@falkirk.gov.uk

Chief Finance Officer contact details: Bryan Smail, Chief Finance Officer, Falkirk Council, Municipal Buildings, FK1 5RS. 01324 506301 bryan.smail@falkirk.gov.uk
Country:
 England
 Scotland
 Wales
 Northern Ireland

Please provide the name of any consultancy companies involved in the preparation of the bid:
Stantec UK Ltd
For bids from Northern Ireland applicants please confirm type of organisation
 Northern Ireland Executive	Third Sector
 Public Sector Body	Private Sector
 District Council	Other (please state)

PART 1 GATEWAY CRITERIA / Failure to meet the criteria below will result in an application not being taken forward in this funding round
1a Gateway Criteria for all bids / Please tick the box to confirm that your bid includes plans for some LUF expenditure in 2021-22 / Please ensure that you evidenced this in the financial case / profile.	Yes / No
1b Gateway Criteria for private and third sector organisations in Northern Ireland bids only / Please confirm that you have attached last two years of audited accounts.	Yes / No
Northern Ireland bids only Please provide evidence of the delivery team having experience of delivering two capital projects of similar size and scale in the last five years. (Limit 250 words)

PART 2 EQUALITY AND DIVERSITY ANALYSIS
2a Please describe how equalities impacts of your proposal have been considered, the relevant affected groups based on protected characteristics, and any measures you propose to implement in response to these impacts. (500 words)
Falkirk Council is committed to promoting fairness, dignity, respect and equal opportunities for all who live, work in or visit the Falkirk Council area. Our approach is to promote equality based on rights and responsibilities. Falkirk Council has identified key equality and diversity challenges facing those that live and work in the area and those who visit it, including : / Inequality of opportunity and of outcomes as a result of poverty and deprivation, predominantly in urban areas. / A disproportionately larger, ageing population and related health/ disability issues. / Rural and social isolation, specifically among particular sections of the community, e.g. older people. / The Council have considered the impacts of its proposal on addressing these issues and how they affect groups based on protected characteristics. In particular, it is expected the proposals will positively address these issues. / A99/A904 Dualling, Westfield Roundabout Upgrade & New Roundabout Accesses / The aim of these investments is two-fold: improving the flow & management of traffic in the area, and enabling the development of adjacent sites through the provision of access roundabouts. As such, they are unlikely to have a direct impact on specific characteristics. However, through the housing and commercial developments that they enable it is expected that they will have a positive indirect impact on adjacent urban areas facing high levels of deprivation. / Improved pedestrian and cycle crossing facilities, by way of an iconic elevated bridge structure / The new active travel infrastructure will provide facilities that support low-cost forms of transport, improving access employment and education opportunities. The new bridge will also connect with the Falkirk Active Travel Hub which regularly holds themed rides and maintenance sessions with targeted groups who are expected to benefit from the upgraded routes. The targeted grounds include; disabled riders, a Muslim Women’s Group and Falkirk Belles Women Riders Group. The Hub is fully engaged in the project and will be one of the main organisational beneficiaries that will promote use of the routes to those groups of users and individual clients. / The investment is expected to provide a facilitative asset that makes active travel easy and safer for all. The new elevated crossings will also reduce the risk of accidents for cyclists which is presently a threat with the at-grade crossing. / Section 149 of The Equality Act 2010 requires Falkirk Council to have due regard: / Eliminate discrimination, harassment and victimisation / Advance equality of opportunity between those who have protected characteristics and those who don’t / Foster good relations between those who have protected characteristics and those who don’t / Significant design time has gone into ensuring wheelchair access and low gradient for less abled users, hence the spiral ramp features. / The Council’s project governance structure, communications and engagement plan for the project encourages partners and communities to share expertise and experience. Records of meetings will be maintained and feedback acted on. Engagement with different parts of the community will afford the project team a detailed appreciation of community opinions influence project design, delivery and operation.

When authorities submit a bid for funding to the UKG, as part of the Government’s commitment to greater openness in the public sector under the Freedom of Information Act 2000 and the Environmental Information Regulations 2004, they must also publish a version excluding any commercially sensitive information on their own website within five working days of the announcement of successful bids by UKG. UKG reserves the right to deem the bid as non-compliant if this is not adhered to. / Please specify the weblink where this bid will be published: www.falkirk.gov.uk/levelup

PART 3 BID SUMMARY
3a Please specify the type of bid you are submitting	Single Bid (one project) / Package Bid (up to 3 multiple complimentary projects)
3b Please provide an overview of the bid proposal. Where bids have multiple components (package bids) you should clearly explain how the component elements are aligned with each other and represent a coherent set of interventions (Limit 500 words).
The Westfield Roundabout is next to the Falkirk Stadium at the intersection of the A9 and the A904. The 4-way junction is on an important gateway route into Falkirk as well as the main link between Falkirk, M9 Junction 6 and Grangemouth. It is heavily trafficked and a regular pinch point. The area of intervention is shown below. / Over the last decade, development nearby including Falkirk Stadium, the Helix and the recently completed Forth Valley College Campus, has significantly increased traffic volumes. Junction analysis has demonstrated the existing roundabout and signal-controlled crossroads have insufficient operational capacity to accommodate the 2024 base plus development traffic demand[1]. This is a barrier to housing development in the area and raises abnormal costs associated with development. This has impacted on Falkirk’s ability to meet its housing need (see 5.1). / Effective use and improved connectivity between these key economic assets, including the undeveloped Falkirk Gateway site adjacent, is central to ‘levelling up’ Falkirk. Investment now will help support the area’s economic recovery from COVID-19. / Falkirk Council is seeking LUF of £20million to deliver proposed improvements in 4 stages aligned to the ongoing development of this part of Falkirk: / Dual carriageway upgrading to the A904, from M9 Junction 6 (Earlsgate) to Forth Valley College; and to the A9 from the Etna Road (Helix Park) roundabout to the Falkirk Stadium roundabout / Three new roundabouts at Middlefield Road, West Mains Road and serving the proposed Falkirk Gateway development site / An upgraded A9/A904 roundabout, Westfield Roundabout / Improved pedestrian and cycle crossing facilities, by way of an iconic elevated bridge structure / See Appendix 1 – Design Package for details. / Critically, the fourth element will provide a cycle and pedestrian network across the 4 quadrants of the A9 / A904 junction and along their spurs. The 4 quadrants include: / • Helix Park (home of The Kelpies), / • Falkirk Community Stadium / Low-Carbon-Vehicle (LCV) Hub / • Falkirk Gateway North / Forth Valley College / • Falkirk Gateway South / The network will comprise a bridge and 4,200m of shared path/cycleway, including the bridge structure and ramps. It will deliver seamless active travel options across the fastest growing part of Falkirk/ Grangemouth and provide effective connections to existing active travel routes. With some 36,000 monthly non-motorised user (NMU) visitors to Helix Park, the bridge is an important part of the works, ensuring safety and connectivity are paramount considerations. / Westfield Roundabout Proposals / Project phasing will reflect the active travel and transport requirements of key sites, and particularly Falkirk Gateway North & South. The extended works will ensure potential pinch points beyond the junction are also addressed. Project delivery will see implementation of a comprehensive strategic approach to enhancing traffic flows between the M9, Falkirk and its main gateway. / Helix / Former College Site / Iconic Active Travel Bridge / Westfield Roundabout / A9 / A904 / West Mains Roundabout / Middlefield Roundabout / Gateway Site / Gateway Roundabout / Etna Roundabout
3c Please set out the value of capital grant being requested from UK Government (UKG) (£). This should align with the financial case:			£20million
3d Please specify the proportion of funding requested for each of the Fund’s three investment themes	Regeneration and town centre		0%
	Cultural		0%
	Transport		100%
PART 4 STRATEGIC FIT
4.1 Member of Parliament Endorsement (GB Only) / See technical note section 5 for Role of MP in bidding and Table 1 for further guidance.
4.1a Have any MPs formally endorsed this bid? If so confirm name and constituency. Please ensure you have attached the MP’s endorsement letter.		Yes / No

4.2 Stakeholder Engagement and Support / See technical note Table 1 for further guidance.
4.2a Describe what engagement you have undertaken with local stakeholders and the community (communities, civic society, private sector and local businesses) to inform your bid and what support you have from them. (Limit 500 words)
Formal consultation started with submission of a proposal of application notice on 14th August 2019. The public consultation event was advertised in the Falkirk Herald (14th September 2019.) Postcard notifications were also sent to local residents and businesses, and notifications publicising the public event posted on social media accounts. The consultation was held on 3 October 2019 at Forth Valley College. / Attendees were encouraged to complete feedback forms to capture their views of the proposed scheme. 124 feedback forms were received on or after the event. Analysis of the responses showed: / 96% have a clear understanding of the project; / The most common current means of travel along the route is by motor vehicle (43%), followed by walking and cycling; / Reducing congestions is the most important priority (29%) followed by safety (27%); / 69% rate the project favourably for providing improved connectivity to active travel routes (either ‘very good’ or ‘good’); / 73% of responses view the project as beneficial compared with the current situation. / Key themes emerging from the consultation included: the impact of the proposed scheme on traffic flow; how local residents safety concerns will be addressed; design and cost suggestions; and environmental effects. Various other questions were asked regarding issues such as funding, access and egress from local roads, maintenance, provision for disabled users and environmental considerations. / Other issues raised included; advanced notice of any road closures and diversions, potential for anti-social behaviour, parking, access to local amenities; facilities for non-motorised users (e.g. crossings); interface with below ground services; landscape design; and loss of passing trade during construction. / Subsequent design has been informed by the consultation responses. Examples of design responses are shown below / Example Issue Response / Project will not improve congestion Vehicle movements are expected to increase in the area by 25-30% as a result of neighbouring / developments and future traffic. The project will introduce traffic signals and dedicated turning facilities and remove uncontrolled crossings at Westfield roundabout. This will effectively control traffic flow and reduce queue lengths. / Not enough space for cyclists to manoeuvre on bridge Westfield Bridge bridges and ramps have been designed & will be delivered to appropriate design standards. They are shared use with good visibility to avoid manoeuvring issues for users. There will also be grade- separated pedestrian/cyclist connectivity between all quadrants of Westfield roundabout. / A decision on the planning application is expected in July 2021. No objections have been raised by statutory stakeholders[2] [3] including: / Falkirk Council: / Roads Development, Transport Planning and Flooding Units / Planning and Environment Unit / Environmental Protection Unit / Transport Scotland / Scottish Environment Protection Agency / Scottish Rights Of Way And Access Society / Scottish Water / Network Rail / National Architectural Liaison Support & Development Officer / Coal Standing Advice Area / Biodiversity Officer - Planning and Environment / Museum Service / Scottish Natural Heritage
4.2b Are any aspects of your proposal controversial or not supported by the whole community? Please provide a brief summary, including any campaigns or particular groups in support or opposition? (Limit 250 words)
The volume and nature of consultation feedback demonstrates that project information is well understood and that community engagement was conducted successfully. / Some 73% of responses viewed the proposed scheme as beneficial compared to the current situation, while 27% who disagreed. There are no campaigns or particular groups in opposition to the plans. / There was a positive and supportive response from attendees of the public consultation e.g. improved road capacity, roundabouts pedestrian/cyclist safety etc. including all of the positive impacts identified in the consultation responses. / Where possible, the Design Team has responded to concerns raised. Improvements to the A9/A904 roundabout are supported within LDP2 (2020)[4], and the LDP2 also identifies Falkirk Gateway and the former Forth Valley College site as Strategic Growth Areas. / Because of the LDP2 policy support and the information obtained through the public consultation it is not anticipated that there will be any substantial opposition to the delivery of the project.
4.2c Where the bidding local authority does not have the statutory responsibility for the delivery of projects, have you appended a letter from the responsible authority or body confirming their support?		Yes / No / N/A
For Northern Ireland transport bids, have you appended a letter of support from the relevant district council		Yes / No / N/A
4.3 The Case for Investment / See technical note Table 1 for further guidance.
4.3a Please provide evidence of the local challenges/barriers to growth and context that the bid is seeking to respond to. (Limit 500 words)
Prior to the COVID-19 pandemic, Falkirk faced significant local challenges and barriers to growth. The Scottish Index of Multiple Deprivation (SIMD) 2020[5] identified: / 35 datazones in the worst 20% in Scotland, 2 more than in 2016 / 15% (24,575) of Falkirk residents are in the 20% most deprived areas in Scotland / 5 datazones in the worst 5% - one more than 2016 / 9 datazones in the worst 6-10% - one less than 2016 / 11 datazones in the worst 16-20% - two more than 2016 / Falkirk Town Centre is ranked 1st in the income domain (i.e. among the lowest incomes in Scotland); and / Bainsford and Langlees, adjacent to Westfield Roundabout rank in the worst percentile of deprived areas in Scotland. / The figure below indicates those areas neighbouring Westfield in the 20% most deprived in Scotland. / A Social Market Foundation report[6] analysed industries, places and groups at greatest medium-term economic risk (2020-2023) as a result of the pandemic. It showed Falkirk in the worst 3 affected areas in Scotland, with 67% and 71% of employment respectively in moderate or severely impacted sectors. / Falkirk’s challenges over the past year are evidenced by the impact on its local labour market. In March 2021, Scotland’s unemployment rate was 6.1% an increase of 86% in a year. Despite housing Scotland’s largest industrial manufacturing concentration (Grangemouth), Falkirk’s economy has seen a similar impact with unemployment increasing by 83% over the past year. Unemployment among those aged 16-24 rose from 675 to 1,260 (87%) [7]. / These infrastructure limitations are a significant barrier to unlocking development sites stalled in some cases since the economic crisis in 2008-12. Addressing these constraints will help rebalance the area’s reliance on a limited number of large manufacturing employers, in turn helping to address the significant rise in local unemployment. / Increasing unemployment is one of the major challenges facing Falkirk and ‘levelling up’ Falkirk’s deprived communities is not going to be easy. Substantial infrastructure investment is needed to support growth. The upgrading of the A904/A9 and associated site access infrastructure is required to facilitate development at the Falkirk Gateway and former College sites. Without enabling access to these sites, the Council will continue to fall short of meeting the areas housing need (See 5.1). The area has also seen a 17% increase on average rent prices in comparison to the national average over of 7% the past 5 year. As a Strategic Growth Area for Falkirk new housing on these sites will accommodate 271 new homes, helping to reduce rent pressure in the area.
4.3b Explain why Government investment is needed (what is the market failure)? (Limit 250 words)
Falkirk faces significant transport and related environmental challenges for pedestrians, drivers and public transport users. The existing design approach prioritises vehicular movement which frustrates commitments to promoting active modes such as walking and cycling, and the reliance on motor vehicles impacts negatively on air quality. Road users generally do not consider impacts on others in deciding to drive. As a result, they create ‘negative externalities’ i.e. pollution, which leads to environmental degradation. Quality of environment directly influences Falkirk’s attractiveness to residents and visitors. These factors also influence the extent to which an investment-friendly environment can be established, fundamental to addressing identified the deep-rooted challenges. The effect is to reduce the attractiveness of investment in future employment opportunities at the Gateway, travel to and from the Gateway, Helix, Forth Valley College and the town centre throughout the day. / Across Falkirk, development is hampered by infrastructure constraints such as the Westfield Roundabout. Abnormal costs undermine viability for commercial, residential, industrial and other properties. A failure to meet housing demand has prevented the area from achieving its potential and has played a role in exacerbating the deprivation effects outlined above. Unlocking central sites such as Falkirk Gateway and the Former College site by addressing viability constraints will help deliver much needed housing to support the sustainable growth and ‘levelling up’ of Falkirk. / LUF investment is needed to address the market failure present on the Falkirk Gateway and former College sites by providing the enabling infrastructure required to unlock them and eliminate development constraints.
4.3c Please set out a clear explanation on what you are proposing to invest in and why the proposed interventions in the bid will address those challenges and barriers with evidence to support that explanation. As part of this, we would expect to understand the rationale for the location. (Limit 500 words)
The project has 4 stages aligned to the related development of surrounding sites and the needs of neighbouring communities. See to Appendix 1 – Design Package. / (1) Dual carriageway upgrade: to the A904, from M9 Junction 6 (Earlsgate) to Forth Valley College; and to the A9 from the Etna Road (Helix Park) roundabout to the Falkirk Stadium roundabout. (2) An upgraded A9/A904 roundabout, Westfield Roundabout. / The dual carriageway will reduce congestion and travel times along this arterial route. Introduction of traffic signals and dedicated turning facilities and removal of uncontrolled crossings will improve traffic flow and reduce queue lengths. Segregated left turn lanes on all 4 arms will also improve traffic flow. This will improve the effective flow of vehicles throughout the area, enabling development of neighbouring stalled sites (i.e. Falkirk Gateway, Stadium & Former College site). It also has the potential to generate environmental benefits through more efficient traffic flows and reduced congestion. / (2) New roundabouts at Middlefield Road, West Mains Road and serving the proposed Falkirk Gateway site / Initially the new roundabouts on the A904 will enable access to the northern section of the Falkirk Gateway site (see Appendix 2 – Falkirk Gateway Masterplan). As per the development agreement, requiring the Council to provide specification for the Council Gateway Enabling Works (access roundabout and Sustainable Urban Drainage System), the access will allow the development of up to 17,822 sqm. of retail & leisure uses and up to 71 residential units (including 17 affordable). / The Middlefield Road roundabout between Westfield Roundabout and Falkirk town centre, will enable a secondary access to the Former College Site. In conjunction with the upgrade of Westfield and connecting A9/A904 roads, LUF investment will enable delivery of 200 new homes. / (3) Improved pedestrian and cycle crossing facilities, by way of an iconic elevated bridge structure / Pedestrian and cyclists are at the centre of the project and will benefit in several ways. Access to the new College Campus, Falkirk Stadium, Helix Park and future development sites will support future growth and create a central hub for green and active travel routes across Falkirk and Grangemouth. The Council’s car park on the east of the A904 is regularly used as overspill to accommodate the higher than anticipated growth in visitor numbers coming to the Kelpies & Helix. The Helix is also an important resource for local communities and Falkirk residents, so improved access to it would have major local benefits. / The active travel infrastructure is also important for its integration with project propositions within the Falkirk and Grangemouth Investment Zone package of works (see 4.4c). / With circa 36,000 monthly non-motorised user (NMU) visitors to Helix Park, the bridge will provide significant safety and connectivity improvements. Currently, the Stadium carpark is frequently used as overspill to accommodate the higher than anticipated number of visitors to the Kelpies and Helix. The configuration requires pedestrians and cyclists coming from the Stadium to use an at-grade crossing on an arterial route, which introduces risk of accident between vehicles and cyclists or pedestrians.
4.3d For Transport Bids: Have you provided an Option Assessment Report (OAR)		Yes / No
4.3e Please explain how you will deliver the outputs and confirm how results are likely to flow from the interventions. This should be demonstrated through a well-evidenced Theory of Change. Further guidance on producing a Theory of Change can be found within HM Treasury’s Magenta Book (page 24, section 2.2.1) and MHCLG’s appraisal guidance. (Limit 500 words)
The need for the project and options for its delivery were assessed during the preparation of the Falkirk TIF Business Case (2013). Subsequent works have been undertaken to assess detailed design options for these works and confirm the proposed solution addresses capacity upgrade requirements and on-site constraints, including ground conditions and utilities. / The logic model below explains the delivery of the project outputs and impacts will flow from the interventions supported by LUF investment. and public sector co-funding
4.4 Alignment with the local and national context / See technical note Table 1 for further guidance.
4.4a Explain how your bid aligns to and supports relevant local strategies (such as Local Plans, local economic strategies or Local Transport Plans) and local objectives for investment, improving infrastructure and levelling up. (Limit 500 words)
Policy/Strategy Contribution / Falkirk LDP 2 (2020)[8] LDP2 identifies the need for substantial infrastructure investment to support growth, including upgrade of Westfield Roundabout and A9/A904 approach roads. It also identifies Falkirk Gateway (MU16), including redevelopment of the old college site (H41) as a Strategic Growth Area, which could accommodate 300 new homes. / Falkirk Economic Recovery Plan (2020) [9] The project supports the areas recovery plan, contributing to Communities, Housing & Infrastructure Item 4 - Delivery of A904/Westfield Bridge and Roads infrastructure. / Falkirk’s Economic Strategy (2015-2025) [10] The project directly creates opportunities for investment through “supporting infrastructure to enable ready access to sites, premises”. The strategy particularly references the Falkirk Gateway as an ‘”exciting ‘placemaking’ initiative that will build on the success of ventures such as the Helix, the Falkirk Community Stadium and the development of the new Forth Valley College Campus”. / Falkirk Grangemouth Investment Zone (FGIZ)[11] The project will directly support the £90million FGIZ deal complementing investments in: / Industrial innovation: by improving strategic connectivity and Falkirk’s attractiveness as a place to invest, particularly in the sustainable development of its manufacturing base. / Infrastructure: by directly supporting enhanced connectivity between economic assets and key local industries such as construction, logistics, manufacturing, tourism and their supply chains. / Place: by enhancing connectivity between Falkirk & Grangemouth and their town centres. The new iconic bridge will provide more direct and safer access to the Helix Park (now one of Scotland’s best visited attractions). Links to neighbouring disadvantaged areas will be improved, encouraging active travel and outdoor activity. The new active travel bridge will also support redevelopment of Grahamston Station as a public transport interchange consolidating bus, rail and active travel in a central location. It will directly facilitate the creation of a green corridor between Falkirk and Grangemouth Town Centres to increase community linkages and cohesion / Local Transport Strategy (2014)[12] The project directly contributes to Objective 1 by improving journey times and connections through tackling the congestion which impacts delivery against the area’s economic growth objectives. It contributes to Objective 2 by provision of accessible transport options (Westfield Bridge), particularly to disadvantaged communities (Bainsford). The new iconic active travel bridge will also contribute to Objectives 3 & 4 by encouraging more active travel users, as well as improving users safety. / Road Safety Plan (2014) [13] The project directly contributes to Plan delivery through: / Improved safety through pedestrian/cyclist segregation from motorised traffic with integrated shallow drainage features between the carriageway and shared-use pathways / Grade separated pedestrian/ cyclist connectivity across Westfield Roundabout / Staggered signal controlled crossings over the dual carriageway allowing safe pedestrian/cyclist crossing / Improved safety of public transport users, enabling buses to enter lay-bys before passengers board or alight / The bid aligns to and supports Scottish Planning Policy by creating ‘better places’ though a collaborative process that include design development, renewal and regeneration of the built & urban environment. The project has been designed to deliver ‘well-connected’ places
4.4b Explain how the bid aligns to and supports the UK Government policy objectives, legal and statutory commitments, such as delivering Net Zero carbon emissions and improving air quality. Bids for transport projects in particular should clearly explain their carbon benefits. (Limit 250 words)
The proposal aligns the Levelling Up Fund guidance for transport projects by delivering high-quality active travel infrastructure and upgrades/improvements to the local road network. These interventions will support economic growth, reduce congestion, and improve the experience of transport users. / Enhancing walking and cycling routes between Falkirk and Grangemouth, and improving links to Forth Valley College, The Helix , Falkirk Stadium and new development areas is a principal focus of this project. It directly aligns to and supports Net Zero ambitions by investing in improved pedestrian and cycling infrastructure. It is expected this will encourage more people to travel by bike or on foot for everyday journeys as well as improving accessibility to town centres and green networks. / The project has been designed consistent with the Design Manual for Roads and Bridges, appropriate for supporting the urban environments contribution to Net Zero. The A9 A904 improvements will introduce areas to attenuate Surface Water Runoff so it can be released at a natural rate to watercourses. Additionally, Surface Water Runoff will be collected using Sustainable Drainage components which will provide Pollution Risk mitigation at source. The concept of a ‘self-powering’ bridge including energy efficient LED lighting plus the potential for energy generation in the structure has been factored into the design. The bridge deck will house discreet drainage which will collect rainwater and channel it to the development’s sustainable urban drainage system. Alternative materials which require less carbon in production and operation will be promoted where possible.
4.4c Where applicable explain how the bid complements / or aligns to and supports other investments from different funding streams. (Limit 250 words)
Falkirk Council's £67 million Tax Incremental Financing (TIF) scheme is expected to bring private investment of £413 million to the area, creating almost 6,000 jobs and hundreds of apprenticeships. The Council funds TIF improvements by borrowing against future business rate income from enabled development. The Westfield Roundabout and A9/A904 is one of the main strategic M9 Corridor investments. TIF will make a funding contribution of £31.6 million to project delivery. / On 21 July 2020, the UK and Scottish Governments announced a Growth Deal package of £90 million for delivery of the Falkirk-Grangemouth Investment Zone. / Growth Deal Theme LUF Contribution / Infrastructure including roads, rail and ports projects to support industries such as construction, logistics, manufacturing, tourism and their supply chains. The infrastructure proposed in this bid directly invests in and reinforces the areas strategic infrastructure that will support Falkirk’s key industries and their supply chains. / Industrial innovation: particularly industrial biotechnology, carbon capture and autobus innovation to enable the transition to more sustainable industries whilst preserving our manufacturing base. Through opening up access to commercial and residential sites, the infrastructure proposed in this bid complements ‘Industrial innovation’ through providing additional ‘grow-on’ space and homes for the areas labour market respectively. / Place: to enhance our town centres and the tourism sector. Development of the iconic elevated bridge will enhance connectivity between Falkirk’s key tourism assets (e.g. Helix), Grangemouth and Falkirk town centre. The new active travel bridge will also support redevelopment of Grahamston Station
4.4d Please explain how the bid aligns to and supports the Government’s expectation that all local road projects will deliver or improve cycling and walking infrastructure and include bus priority measures (unless it can be shown that there is little or no need to do so). Cycling elements of proposals should follow the Government’s cycling design guidance which sets out the standards required. (Limit 250 words)
WSP was appointed by Falkirk Council in 2015 to examine the feasibility of options for the proposed Eastern Gateway Crossing (i.e. Westfield Roundabout) . A high-level options appraisal was produced examining crossing designs compliant with cycling design guidance and required standards. / Westfield Bridge’s bridges and ramps have been designed as shared use with good visibility and step-free access. The 5m bridge deck width meets design standards and Sustrans requirements for a shared pedestrian and cycle route. The proposed 3m wide ramps meet the requirements of the Equality Act and the Transport Scotland[14]. The feasibility report proposes a compliant design with 5m lengths of 1:15 ramps interspersed with 1.5m long landings. Ramp length is dictated by the allowable rise and the required final bridge clearance (5.7m to soffit level). / In addition to the development of a dual carriageway on the A9/A904, consideration will be given to active users through integration of various path networks and associated underpasses. Cyclists will benefit from the proposed scheme and connectivity throughout will be maintained and improved. Cycle connections will be provided to the immediate area around Westfield roundabout as well as the wider area including the Forth Valley College Campus, Earl’s Gate roundabout and Green Corridor. The scheme will provide a cycle connection between Earls Gate roundabout and Falkirk town centre.
[1] Transport Appraisal
[2] P/20/0545/FUL | A9/A904 Public Consultees Available at: https://edevelopment.falkirk.gov.uk/online/applicationDetails.do?activeTab=consulteeComments&keyVal=QJXKU9HCFUP00
[3] P/20/0545/FUL | A9/A904 Road Improvements and Associated Earthworks, Landscaping and Surface Water Drainage Works | Westfield Roundabout, Falkirk & Earls Gate Roundabout, Grangemouth. Available at: https://edevelopment.falkirk.gov.uk/online/applicationDetails.do?activeTab=consulteeComments&keyVal=QJXKU9HCFUP00
[4] Available at: https://www.falkirk.gov.uk/services/planning-building/planning-policy/local-development-plan/docs/ldp2/LDP2.pdf?v=202101191030
[5] Scottish Index of Multiple Deprivation (SIMD). Available at: https://www.falkirk.gov.uk/services/council-democracy/statistics-census/simd.aspx
[6] ‘Levelling Down’. Available at: https://www.smf.co.uk/wp-content/uploads/2020/07/Levelling-down-medium-term-economic-impact-of-coronavirus-Jul-2020.pdf n
[7] Falkirk Council Economic Information Analysis. Available at: https://www.falkirk.gov.uk/services/council-democracy/statistics-census/simd.aspx
[8] Available at: https://www.falkirk.gov.uk/services/planning-building/planning-policy/local-development-plan/docs/ldp2/LDP2.pdf?v=202101191030
[9] Available at: https://www.falkirk.gov.uk/services/business-investment/policies-strategies/falkirk-economic-strategy.aspx
[10] Available at: https://www.falkirk.gov.uk/services/business-investment/policies-strategies/falkirk-economic-strategy.aspx
[11] Available at: https://www.falkirk.gov.uk/services/business-investment/falkirk-grangemouth.aspx
[12] Available at: https://www.falkirk.gov.uk/services/roads-parking-transport/policies-strategies/transport-policy.aspx
[13] Available at: https://www.falkirk.gov.uk/services/roads-parking-transport/policies-strategies/transport-policy.aspx
[14] Cycling by Design (2010, Revision 2011)

PART 5 VALUE FOR MONEY
5.1 Appropriateness of data sources and evidence / See technical note Annex B and Table 1 for further guidance. / All costs and benefits must be compliant or in line with HMT’s Green Book, DfT Transport Analysis Guidance and MHCLG Appraisal Guidance.
5.1a Please use up to date evidence to demonstrate the scale and significance of local problems and issues. (Limit 250 words)
Westfield Roundabout & junction analysis has demonstrated the existing roundabout and signal-controlled crossroads have insufficient capacity to accommodate the 2024 base plus development traffic demand[15]. / The A9/A904 is an arterial route through Falkirk, linking key areas of economic activity which underpin development of the area’s industrial and distribution sectors. Congestion prevents the effective movement of goods (HGV’s) and people (labour) through the area. The A9/A904 also severs town centre, resident and business populations from employment and education opportunities in the west (Bankside Industrial & Forth Valley College) and employment and leisure opportunities in the east (Earlsgate, Grangemouth & the Helix) [16]. / Falkirk will experience continued population and household growth to 2030, the period of its LDP2. By 2039, the population is expected to increase by 7% to 170,870. Household numbers are forecast to rise by 10,641 between 2014 and 2039[17]. To facilitate growth, a target of 6,894 new homes has been set by LDP2. Delivery levels are below the level required as shown below. / 2017-20 Delivery Average Annual Delivery 2017-30 Need Annual Need Annual Shortfall Current Total Shortfall / Falkirk 1,350 450 6,894 530 80 241 / People's experience of poverty, material deprivation (See 4.3a) and housing circumstances are intertwined. The sites enabled by the LUF funded infrastructure have a capacity to support up to 200 homes and will directly contribute to meeting the area’s need as well as improving the areas high-levels of deprivation.
5.1b Bids should demonstrate the quality assurance of data analysis and evidence for explaining the scale and significance of local problems and issues. Please demonstrate how any data, surveys and evidence is robust, up to date and unbiased. (Limit 500 words)
Socioeconomic Issues / The analysis of socioeconomic issues is based on publicly available statistics published by the Scottish or UK Governments. The data underpinning the economic appraisal is specific to Falkirk wherever possible. This includes: / Build cost estimate data (sourced from BCIS) / House price data (sourced from Scottish Government) / Non-residential rental rates (sourced from valuation report) / Using data specific to the project area ensures the local context is captured within the analysis and impact estimates are accurate and proportionate to the project’s area of influence. / Stakeholder engagement has been undertaken to obtain community input and feedback. Key themes of discussion from the consultation included: the impact of the proposed scheme on traffic flow; how local residents safety concerns will be addressed; design and cost suggestions; and environmental effects. Various other questions were asked regarding issues such as funding, access and egress from local roads, maintenance, provision for disabled users and environmental considerations. Please see section 4.2a for more details on the stakeholder consultation process and findings. / Viability and Gross Development Value / The Council commissioned independent cost estimates and valuations of the proposed development. WSP produced a summary of cost estimates in November 2020. The project valuation was produced by District Valuers Services, part of the Valuation Office Agency. The valuers are suitably experienced and qualified and have detailed current and local knowledge of the markets applicable to the project. / Market housing price estimates have been obtained from Zoopla and are current at June 2021. / Residential rental rates for the Forth Valley rental market area are sourced from Scottish Government Private Sector Rent Statistics (2010-2020). / Select Sizes: Fourth Valley Medium Values (£ monthly) / 2017 2018 2019 2020 Falkirk Increase on 2017 Scottish Increase on 2017 / 1 Bedroom Properties 395 400 420 415 5% 5% / 2 Bedroom Properties 550 575 575 595 8% 5% / 3 Bedroom Properties 695 750 750 795 14% 6% / 4 Bedroom Properties 995 1,000 1,100 1,325 33% 13% / All 595 617 637 698 17% 7% / Affordable rental rates have been calculated at 80% of market rates, as this represents the maximum value which could be charged for affordable housing[18].
5.1c Please demonstrate that data and evidence chosen is appropriate to the area of influence of the interventions. (Limit 250 words)
Data and evidence specific to the development site or Falkirk has been used in the first instance. Where data is not available at this level of specificity, local authority data has been used. The data and evidence used in this analysis includes: / Scottish Index of Multiple Deprivation (SIMD) 2020 – Lower Super Output Areas (e.g. Bainsford) / Data related the number of housing units and commercial floorspace for the wider LVU land calculations are from the Falkirk Middlefield Intermediate Zone (2011). / Worker turnover and productivity values are based at the Falkirk (Local Authority) level / Employment densities obtained from Employment Density Guide (3rd Edition), based on indicative use classifications detailed in the masterplan / Community consultation specific to this project was conducted in Autumn 2019 at Forth Valley College / As shown in the response to Section 4.2, the Council has carried out consultation with the local community and the wider public to record the issues they have in the area. This has influenced the design of the infrastructure proposed in the bid. The Council has also engaged locally through its LDP2 which highlights a need for the Westfield A9/A904 infrastructure.
Effectiveness of proposal in addressing problems
5.2a Please provide analysis and evidence to demonstrate how the proposal will address existing or anticipated future problems. Quantifiable impacts should usually be forecasted using a suitable model. (Limit 500 words)
LUF supported roadworks will reduce congestion on a main arterial route and improve travel times. Without these, road network congestion will prevent efficient movement of goods and people through the area. Dualling sections of the A904 and A9 will facilitate the movement of vehicles between key areas, including the Stadium, Grangemouth, the Helix, Forth Valley College, West Mains, Earlgate Park, and Grangemouth Port. / The introduction of a raised active travel bridge above the Westfield Roundabout will create a new and iconic feature to support modal shift to active travel. / Up-to-date modelling by WSP has shown that a solution with at-grade crossings does exist in theoretical capacity terms. However, introducing traffic signal control and a new bridge for non-motorised-users (NMUs) at the Westfield Roundabout connecting the four quadrants has emerged from previous work as the preferred option, and the wider scheme has been subject to public consultation assuming this was the case. This layout improves the safety of all road users by separating vehicles and NMUs and could provide attractive routes between new developments and existing facilities The inclusion of this bridge will increase accessibility to key sites in Falkirk for pedestrians and cyclists. By separating pedestrian and cycle routes from road user, the bridge will reduce the risk of accidents between pedestrians/cyclists and vehicles, providing for safer journeys and more enjoyable trips. / Analysis shows that for pedestrians, all routes are faster via the bridge. For wheelchair and mobility scooter users, the at-grade crossings are quicker and shorter that the bridge, however this does not take into account the quality or perceived safety of the journey. For cyclists, similar to pedestrians, all routes are faster via the bridge. / WSP’s junction analysis results have demonstrated that the existing roundabout and signal-controlled crossroads have insufficient operational capacity to accommodate the 2024 base plus development traffic demand. However, the introduction of signal control to the roundabout and inclusion of segregated left turn slip lanes on the westbound, northbound and southbound approaches are / predicted to provide sufficient operational capacity to accommodate the 2024 base plus development traffic demand. In addition, the inclusion of left slips also allow pedestrians to cross the roundabout in a ‘walk-with traffic’ manner, without causing problems with internal queueing on the roundabout. / As such, LUF funding to deliver these proposals will enable 271 new residential units, 65 of which will be affordable homes. This will help meet local housing demand and address the shortfall in housing delivery (see 5.1a) / LUF funded infrastructure will also enable nearly 11,000m2 of commercial floorspace supporting a variety of functions and businesses. Four of these commercial units are of substantial scale (ranging from ~1,400m2 to ~3,700m2) and will be able to accommodate specialised functions. The remaining 9 units detailed in the masterplan are smaller in scale (ranging from 60m2 to ~600m2) and will be able to support small businesses and locally oriented retail offer. / The proposal also includes delivery of a 120-bed hotel. This will support the tourist and visitor economy in the area.
5.2b Please describe the robustness of the forecast assumptions, methodology and model outputs. Key factors to be covered include the quality of the analysis or model (in terms of its accuracy and functionality) (Limit 500 words)
Commercial Floorspace and Housing Units / The outputs presented are based on a detailed masterplan and accommodation schedules developed by Smith Design Associates in March 2021. / Employment Estimates / At this stage there are no formalised agreements for occupiers of the commercial floorspace. As such, assumptions regarding their end use have been applied to enable employment estimates. The four largest units (those with floorspaces of more than 1,000m2) have been assumed as retail warehousing-type use, with a jobs density of 90m2 per job. The remaining units have been designated retail or food & drink uses (as detailed within the masterplan) and conservatively assigned job densities of 18m2 per worker. Job densities have been informed by Employment Density Guide (3rd Edition)[19] and the indicative use classifications of the commercial space as detailed in the Falkirk Gateway masterplan. / Active Travel / Active travel benefits have been modelled using the Department for Transport’s Active Mode Appraisal Toolkit (AMAT). Surveys of pedestrian and cycle counts produced by WSP serve as a baseline, and WSP provided uplift estimates of usage. These figures, along with the quantum of development of the active travel infrastructure as per current designs are then input into the AMAT to estimate the quantified benefit of the active travel infrastructure.
5.3 Economic costs of proposal
5.3a Please explain the economic costs of the bid. Costs should be consistent with the costs in the financial case, but adjusted for the economic case. This should include but not be limited to providing evidence of costs having been adjusted to an appropriate base year and that inflation has been included or taken into account. In addition, please provide detail that cost risks and uncertainty have been considered and adequately quantified. Optimism bias must also be included in the cost estimates in the economic case. (Limit 500 words)
Overview / The funding sought from LUF is £20.0m. The following figures detail the impacts on project funding resulting from the application of optimism bias, inflation, and discounting with reference to the delivery plan. / The total discounted LUF request is £21.4 million, inclusive of inflation and Optimism Bias (OB) at 6%. OB has been estimated at the lower-bound of standard civil engineering because of the advanced stage of project design and costing. The designs have ben costed by WSP with support from Balfour Beatty via the SCAPE process. / The total discounted public sector co-funding is £34.7 million, inclusive of inflation and OB. / Combined, the total discounted cost of the project is £56.1 million, inclusive of inflation and OB. / Discounting / Capital costs have been developed with reference to the delivery programme. These are then discounted to the base year of 2021 at the Green Book recommended rate of 3.5% per annum for the social time preference of money / Inflation / Inflation has been applied to all capital costs at 4.30%. This is based on WSP’s November 2020 costs analysis. / Costs risks and uncertainty / Project costs have been estimated to a high degree of certainty. A summary of cost estimates for the works package was produced by WSP on behalf of Falkirk Council in November 2020. An independent valuation report was prepared on behalf of Falkirk Council by Valuation Office Agency in April 2021. / Optimism Bias (OB) has been assumed at 6% of capital costs within the appraisal. As noted above, this is considered proportionate to the robustness of the cost and valuation estimates obtained, but retains a margin to account for cost inflation or incidental expenditures within the programme.
5.4 Analysis of monetised costs and benefits
5.4a Please describe how the economic benefits have been estimated. These must be categorised according to different impact. Depending on the nature of intervention, there could be land value uplift, air quality benefits, reduce journey times, support economic growth, support employment, or reduce carbon emissions. (Limit 750 words)
Direct Land Value Uplift / Land Value Uplift (LVU) is the difference between new use value and previous use value. / A residual valuation model has calculated the value of land in its new use. Residual land valuation is undertaken by subtracting the costs a developer will incur from the estimated maximum revenue that could be obtained from that land, referred to as Gross Development Value (GDV). / The GDV of project deliverables has been estimated using Falkirk market data sourced from CoStar Properties © database and the Zoopla. / The development costs, fees, and profit associated with new housing have been modelled using the set of assumptions in the accompanying guidance to MHCLG’s Land Value Estimates for Policy Appraisal. / As the development sites are vacant and lack access infrastructure it has been assumed that they effectively have no existing value in their current state. Without investment to unlock the sites they will remain unviable for development. / Furthermore, the interventions delivered by the proposed development are required to enable the follow-on development of the former Forth Valley College site. This site has been allocated for residential development within in the Local Development Plan 2, with a capacity of 200 units. / New land values are assumed to increase at 5% annually as suggested by MHCLG guidance. Benefits are realised in the anticipated opening year of a given development and are discounted to the base year and adjusted for displacement. / Investment in Falkirk’s LUF project is anticipated to deliver £64.2 million in present value direct LVU. / Wider Land Value Uplift / Wider LVU is the indirect impact on land values produced by a nearby investment. It can occur around regeneration or infrastructure projects as these may stimulate economic activity nearby or increase the desirability of the location and thus increase demand for property. / A survey of properties within the local area of the proposed development has identified 2215 residential units with an estimated value of £279.1 million, and some 148,000m2 of commercial floorspace (primarily distribution and warehousing space) with an estimated value of £129.6 million. / We have modelled these properties as increasing in value by 1.5% per annum for 5 years following completion of the proposed development. In a recent literature review MHCLG states that this represents ‘a reasonable ceiling figure’ for wider LVU[20]. The proposed development will deliver new, high quality residential and commercial units alongside enhancements to transport infrastructure to facilitate accessibility, and also enable the development of new commercial and residential sites. The Falkirk Gateway site will create a new residential cluster and community which will be supported by complimentary retail and commercial floorspace. Because of these wide-ranging impacts from the project this level of uplift is considered proportionate given the surrounding development. The overall wider LVU is anticipated to be £30.6 million (PV). / Labour Supply Impacts / An estimated 220 employment opportunities will be supported by the various commercial elements within the proposed development. For employment impacts, the BCR only considers the proportion of jobs estimated to be taken up by workforce (re-)entrants. We have conservatively assumed that 5% of jobs will be taken up by workforce (re-)entrants and have monetised these impacts taking account of the welfare impact of labour market entrants (40%). / Labour supply impacts are anticipated to yield £0.8 million PV over 30 years. / Active Travel Benefits / The delivery of new cycling and pedestrian infrastructure will yield benefits as detailed in the Department for Transport’s Active Mode Appraisal Toolkit (AMAT). These benefits will come in the form of reduction of congestion, reduction of infrastructure maintenance costs, reduction of accidents, improvements to air quality, reduced noise and greenhouse gas pollution, reduced risk of premature death, reduced risk of absenteeism and increased journey ambiance. / In total, the net present value of the active travel benefits generated by the scheme are estimated at £2.5 million over a 10-year period. / Distributional Impacts / The development enabled includes delivery of up to 65 affordable homes. Each of these units will receive a government subsidy to meet the difference between affordable and market rents. This represents a transfer from the public sector to occupants. This will have distributional impacts due to the concentration of occupants of affordable rented homes at the lower end of the income distribution. / The distributional impact of the project has been estimated by recording the income transfer in each year, and multiplying that figure by the number of occupied affordable homes and the discount rate. The distributional impact is £1.4 million PV over 30 years.
5.4b Please complete Tab A and B on the appended excel spreadsheet to demonstrate your: / Tab A - Discounted total costs by funding source (£m) / Tab B – Discounted benefits by category (£m)
5.5 Value for money of proposal
5.5a Please provide a summary of the overall Value for Money of the proposal. This should include reporting of Benefit Cost Ratios. If a Benefit Cost Ratio (BCR) has been estimated there should be a clear explanation of how this is estimated ie a methodology note. Benefit Cost Ratios should be calculated in a way that is consistent with HMT’s Green Book. For non-transport bids it should be consistent with MHCLG’s appraisal guidance. For bids requesting funding for transport projects this should be consistent with DfT Transport Analysis Guidance. (Limit 500 words)
The table below summarises the Value for Money of the Proposal, comparing the net present value benefits against the economic costs. / Category Value / Present value benefits / Direct land value uplift 64.2 / Wider land value uplift 30.6 / Labour supply impacts 0.8 / Active travel impacts 2.3 / Distributional impacts 1.4 / A Total benefits 99.3 / Present value costs / LUF request 20.2 / Optimism Bias 1.1 / B Total LUF cost 21.4 / C Co-funding local authority cost 32.7 / Optimism Bias on co-funding 2.0 / D Total public sector cost 56.1 / E Private sector cost - / Value for money / (A - E) / B BCR on Levelling Up Fund grant 4.6 / (A - E) / D BCR on all public sector costs 1.8 / When considered against the LUF grant, the proposal returns strong value for money. It is anticipated to return £4.60 of benefit for every £1.00 of LUF grant invested, inclusive of Optimism Bias at 6%. / Considered against all public sector costs, the proposal returns good value for money with a BCR of 1.8, indicating that £1.80 of benefits are anticipated for each £1.00 of public sector investment.
5.5b Please describe what other non-monetised impacts the bid will have, and provide a summary of how these have been assessed. (Limit 250 words)
The proposed project will result in non-monetised benefits, including: / Enhanced placemaking: construction of a new pedestrian and cycle bridge will contribute to placemaking by being an iconic structure in its own right, but will also facilitate connections to (and between) areas of interest in the town such as the Helix and Kelpies, the town centres, the stadium, and the new Forth Valley College campus / Enhanced quality of life: the improvements to the road infrastructure (A9/A904, Middlefield and West Mains Roads) will improve vehicular traffic flows, thereby improving journey times and amenity

Land value uplift appraisal methodology relies heavily on market prices, and the private benefits realised by the scheme will depend upon housing sales prices and non-residential rates achieved. Changes to these values will not influence other outputs such as new jobs, enhancements to the environment, or the new housing, employment or public realm space itself, yet may result in an ex-post reduction in VfM. / The principal risks to the VfM are economic downturn, an overvaluation of housing value or non-residential rental rates. The table below shows the impact of the BCR given a reduction in prices achieved. / Assumption BCR (all public sector costs) / House values / 15% reduction; lowest assumption 1.6 / 10% reduction; lower assumption 1.7 / 5% reduction; low assumption 1.7 / 0% change (£225,000); central assumption 1.8 / Wider land value uplift also represents a significant proportion of the total benefits. The table below shows the impact of alternative value uplift rates. / Assumption BCR (all public sector costs) / Annual uplift / 0.5%: low uplift assumption 1.4 / 1.5%: central assumption 1.8 / 2.5%: High uplift assumption 2.2
5.5d For transport bids, we would expect the Appraisal Summary Table, to be completed to enable a full range of transport impacts to be considered. Other material supporting the assessment of the scheme described in this section should be appended to your bid.
While not defined as Falkirk’s ‘major transport bid’, a full Transport Appraisal has been carried out can be found at: P/20/0545/FUL | A9/A904 Road Improvements and Associated Earthworks, Landscaping and Surface Water Drainage Works | Westfield Roundabout, Falkirk & Earls Gate Roundabout, Grangemouth. Available at: https://edevelopment.falkirk.gov.uk/online/files/BDD4217A637DC6363547D94EE0AEE639/pdf/P_20_0545_FUL-Transport_Appraisal-1125590.pdf
[15] Available at: https://edevelopment.falkirk.gov.uk/online/applicationDetails.do?activeTab=documents&keyVal=QJXKU9HCFUP00
[16] Available at: https://edevelopment.falkirk.gov.uk/online/applicationDetails.do?activeTab=documents&keyVal=QJXKU9HCFUP00
[17] Falkirk Local Plan August 2020. Available at: https://www.falkirk.gov.uk/services/planning-building/planning-policy/local-development-plan/docs/ldp2/LDP2.pdf?v=202101191030
[18] October 2010 Spending review. UK Government
[19] Homes & Communities Agency (2015).
[20] See: Bhabra, J. (2020). Wider Land Value Uplift.

PART 6 DELIVERABILITY
6.1 Financial / See technical note Table 1 for further guidance.
6.1a Please summarise below your financial ask of the LUF, and what if any local and third party contributions have been secured (please note that a minimum local (public or private sector) contribution of 10% of the bid costs is encouraged). Please also note that a contribution will be expected from private sector stakeholders, such as developers, if they stand to benefit from a specific bid (Limit 250 words)
Item Cost LUF Public Sector / Site Clearance £389,809 £143,671 £246,138 / Fencing £101,497 £37,409 £64,089 / Road Restraint Systems £787,742 £290,337 £497,405 / Drainage £1,595,977 £588,227 £1,007,750 / Earthworks £3,716,999 £1,369,969 £2,347,030 / Pavements £4,328,392 £1,595,309 £2,733,083 / Kerbs, Footways & Paved Areas £1,694,127 £624,402 £1,069,725 / Traffic Signs & Road Markings £583,604 £215,098 £368,506 / Lighting Columns, Brackets & CCTV Masts £653,206 £240,751 £412,455 / Road Lighting & Traffic Sign electricals £670,000 £246,941 £423,059 / Motorways Communications & Technology - - - / Piling & Embedded Retaining Walls £4,251,666 £1,567,030 £2,684,636 / Structural Concrete £877,094 £323,269 £553,825 / Steelwork £4,746,596 £1,749,446 £2,997,151 / Corrosion Protection £470,628 £173,459 £297,169 / Waterproofing for Structures £259,128 £95,506 £163,622 / Bridge Bearings £68,000 £25,063 £42,937 / Expansion Joints & Sealing - - - / Brickwork, Blockwork & Stonework - - - / Special Structures £150,977 £55,645 £95,331 / Accommodation Works & Works for Statutory Undertakers £2,092,338 £771,170 £1,321,168 / Landscape & Ecology £723,678 £266,725 £456,953 / Maintenance Painting of Steelwork - - - / Preliminaries £4,928,255 £1,816,400 £3,111,856 / Contractors /Overheads and Profit £2,587,334 £953,610 £1,633,724 / Inception / Planning £1,248,418 £460,128 £788,290 / Project / Design (Estimate) £1,408,073 £518,971 £889,102 / Project Management Estimate) £1,854,256 £683,420 £1,170,836 / G.I. 2019 £520,000 £191,656 £328,344 / Risk [per @Risk Output Report P85] £5,736,780 £2,114,396 £3,622,384 / Finalised Pre-Contract Design and Preparation £5,822,309 £2,145,920 £3,676,389 / Inflation £1,997,117 £736,074 £1,261,042 / Total costs £54,264,000 £20,000,000 £34,264,000 / The LUF financial ask is £20.00million, 36.9% of project cost. Co-funding of £34.264 million will come from Falkirk Council’s TIF programme and Low Carbon Travel and Transport (LCTT) Challenge Fund. (£2.40million).
6.1b Please also complete Tabs C and D in the appended excel spreadsheet, setting out details of the costs and spend profile at the project and bid level in the format requested within the excel sheet. The funding detail should be as accurate as possible as it will form the basis for funding agreements. Please note that we would expect all funding provided from the Fund to be spent by 31 March 2024, and, exceptionally, into 2024-25 for larger schemes.

6.1c Please confirm if the bid will be part funded through other third-party funding (public or private sector). If so, please include evidence (i.e. letters, contractual commitments) to show how any third-party contributions are being secured, the level of commitment and when they will become available. The UKG may accept the provision of land from third parties as part of the local contribution towards scheme costs. Where relevant, bidders should provide evidence in the form of an attached letter from an independent valuer to verify the true market value of the land.	Yes / No
6.1d Please explain what if any funding gaps there are, or what further work needs to be done to secure third party funding contributions. (Limit 250 words)
The Westfield Bridge project is one of the main M9 corridor strategic improvement projects. It has been allocated Tax Incremental Finance (TIF) support from Falkirk Council funds by borrowing against future business rates income that should be created by the regeneration and development.
6.1e Please list any other funding applications you have made for this scheme or variants thereof and the outcome of these applications, including any reasons for rejection. (Limit 250 words)
Falkirk Council have secured £2.40million of LCTT funding. The LCTT funded element of the programme will only include the shared cycle/ pedestrian pathway, the 4 ramps, the link bridge and any directly associated preliminary costs. There will be no costs included in the project pertaining to the road network. / Funding from TIF is already in place to support project delivery. No further work is needed to address any funding gaps and the project is shovel-ready subject to LUF investment being secured.
6.1f Please provide information on margins and contingencies that have been allowed for and the rationale behind them. (Limit 250 words)
The contingency within the cost estimate fall under the risk value produced after undertaking a Quantitative Cost Risk Analysis from the output of the Risk Register. A risk process has been adopted by the project team profile relevant risks potentially encountered during the works. A risk register was developed. Each risk item was assigned a minimum, most likely, and maximum risk value as part of a three-point estimate and these values have been formulated with agreed upon budgetary values against the probability of the risk occurring. Once the risk register was finalised, a QCRA was able to be generated using a Monte Carlo analysis, and this have provided the risk figure which is used in the cost estimate. The agreed output from the QCRA is used in the P85 statement.
6.1g Please set out below, what the main financial risks are and how they will be mitigated, including how cost overruns will be dealt with and shared between non-UKG funding partners. (you should cross refer to the Risk Register). (Limit 500 words)
The main financial risks to the project and the proposed mitigation and management procedures are summarised below. / Risk register ref Hazard/Risk Effect / consequence Mitigation / response Action Plan / P12 Tar contaminated road construction Contaminated material has to be removed from site which the higher rate of landfill tax will have to be paid. WSP to work in partnership with Falkirk Council (FC) to identify areas where tar contaminated road construction may exist. This could involve reviews of FC's records/surveys. 1. Determine the extent/location of any tar contamination that may be present within the project boundary. 2. WSP to undertake samples via trial pit/cores to confirm locations where contaminated tar is present and consider whether treatment/re-use of contaminated planning’s is appropriate. 3. Liaise with industry specialists (i.e. SEPA) to ensure the best solution is found. / H5 Utility relocation cost/risk/timescale Delays to ground works Increased cost to scheme WSP to engage with utility providers early into design phase to ensure latest utility information available. ECI to develop proposals and works with utility providers to maximise opportunity. 1. Initiate dialogue with utility providers 2. Identify potential clashes 3. Review diversion/protection proposals and identify opportunities to minimise / E1 Adverse weather conditions - greater than 1 in 10 year storm Delays to ground works. Complaints. Compensation to contractors. Ensure contract documents are robust and identify risk allocation. Engage ECI to enable preparation of suitable construction schedule 1. Identify regional weather conditions 2. Capture risk allocation within contract documents 3. Engage ECI to enable preparation of suitable construction schedule / B5 Inflation above allowance Increase cost Programme regular construction cost updates 1. Capture contingency/risk within overall cost plan 2. Regularly update cost plan at key design stages / G13 NPPF - net gain with regards to scheme biodiversity Overall loss of biodiversity scheme wide Potential impact on programme to develop landscape proposal should first pass not achieve a net gain Collaborate with ecologists and landscape designers to identify opportunities to achieve net gain 1. Identify baseline 2. Develop landscape proposal to maximise planting opportunities 3. Review landscape design prior to construction to identify BNG figures 4. Revise landscape design to capture additional areas of compensatory planting to provide a net gain / Q22 INEOS pipeline impacts on programme and/or constructability of carriageway, drainage, PU diversions and elevated structure. Potential redesign of elements of scheme Costly protection works not accounted for Delay to programme Early engagement with Ineos to establish parameters for protection and adjacent works. 1. Early engagement with Ineos 2. Establish design/construction parameters with Ineos 3. Undertake intrusive works to establish exact line and level of apparatus 4. Develop protection options acceptable to Ineos 5. Identify location of apparatus on all plans to ensure design disciplines take cognisance of presence of apparatus / Please see Appendix 3 for the full Risk Register which contains the comprehensive list of identified project risks.
6.2 Commercial / See technical note Section 4 and Table 1 for further guidance.
6.2a Please summarise your commercial structure, risk allocation and procurement strategy which sets out the rationale for the strategy selected and other options considered and discounted. The procurement route should also be set out with an explanation as to why it is appropriate for a bid of the scale and nature submitted. / Please note - all procurements must be made in accordance with all relevant legal requirements. Applicants must describe their approach to ensuring full compliance in order to discharge their legal duties. (Limit 500 words)
Falkirk Council will be responsible for delivering project infrastructure. Achieving project outcomes is dependent on effective infrastructure delivery, and the follow-on development it enables. This will subsequently drive the scale of benefit delivered to Falkirk’s economy and its people. / The approach is as follows / Construction cost estimate prepared by design team and market tested via SCAPE contract at feasibility stage (concluded December 2020, confirming feasibility and cost assurance) / Through the Early Contractor Involvement (ECI) process, Balfour Beatty has been appointed via Scape Procure Scotland - Civil Engineering & Infrastructure framework contract. / Balfour Beatty is working with WSP’s design team to develop construction programme and costs (SCAPE Pre-construction stage). / The SCAPE Framework has been used reflecting the need for early contractor involvement due to the complexity of the bridge structure. The Council commissioned external legal support to ensure its legal compliance. Falkirk Council’s governance team therefore confirms this a legally compliant route. / As related market testing has been completed through the SCAPE framework, this effectively reduces the programme period ensuring delivery within LUF timescales. Other mechanisms e.g. Design & Build have been considered e.g. but were discounted due to the associated programme impacts, which would require more lengthy procurement, while failing to provide the level of cost certainty afforded by the ECI process facilitated through SCAPE / On the grant of planning permission Balfour Beatty will be appointed as Principal Contractor for Delivery. / Balfour Beatty is contractually committed to completing the joint design work with WSP. This should be extended on completion of the design stage and a finalised programme. / Close consultation with public and private stakeholders and programme coordination has been completed via the planning process, ensuring project delivery without conflict with other operations. / The project will be delivered by a LUF Programme Manager (see 6.3) with project management responsibility for all project elements. LUF-funded infrastructure will be adopted as public assets, including associated footways, cycleways, lighting, greenspace and plot access junctions and links to existing public road infrastructure. / With respect to enabled follow-on development, Falkirk Council has a development agreement in place for the Falkirk Gateway site, predicated on delivering the Westfield Roundabout and A9/A904 infrastructure. The Council is also in negotiation with the developer for the former college site (200 homes). The developer has provided a letter of support (See Appendix 4).
6.3 Management / See technical note Section 4 and Table 1 for further guidance
Delivery Plan: Places are asked to submit a delivery plan which demonstrates: / Clear milestones, key dependencies and interfaces, resource requirements, task durations and contingency. / An understanding of the roles and responsibilities, skills, capability, or capacity needed. / Arrangements for managing any delivery partners and the plan for benefits realisation. / Engagement of developers/ occupiers (where needed) / The strategy for managing stakeholders and considering their interests and influences. / Confirmation of any powers or consents needed, and statutory approvals eg Planning permission and details of information of ownership or agreements of land/ assets needed to deliver the bid with evidence / Please also list any powers / consents etc needed/ obtained, details of date acquired, challenge period (if applicable) and date of expiry of powers and conditions attached to them. / 6.3a Please summarise the delivery plan, with reference to the above (Limit 500 words)
A management and delivery plan which builds on that being employed in delivering Falkirk Council’s TIF programme will be used. The delivery and management structure will be separated into three tiers: / High level monitoring and governance by the TIF Executive, as in the TIF legal agreement. The TIF executive includes representatives from the Scottish Government, Scottish Futures Trust, and Falkirk Council, and provides clear governance over the TIF process. For Falkirk Council, this governance level will report to elected members via the relevant Committees. / Ongoing strategic management through the TIF Steering Group. This incorporates senior management of Falkirk Council and representation from Scottish Futures Trust and Scottish Enterprise. The management committee will retain close contact with other stakeholders who will inform strategic delivery / Operational management of project delivery will be within the remit of the TIF Delivery Team. The team will be resourced by officers of the respective specialist departments in Falkirk Council. / The Governance Structure will ensure co-ordination of LUF projects with interventions coming forward via other mechanisms (e.g. TIF, CRF, Growth Deal). This will ensure appropriate resources are identified and allocated to enable project delivery within LUF timescales and to the agreed Project Plan. / The Project Delivery Team will meet monthly to monitor and evaluate project delivery against established milestones and benchmarks, auditing and evidencing all money spent for record keeping and audit trail purposes. Project specific management measures will ensure delivery is aligned with the agreed Delivery Plan. / The TIF Steering Group meets every 4 months and monitors progress of TIF projects via communications and progress reports provided by the Project Delivery Team. Management in this layer will ensure project progress to agreed milestones and that spend is being appropriately monitored for audit. / The TIF Executive meets every 6 months, responsible for monitoring the overall TIF programme. The TIF Executive will receive relevant progress reports and updates from the TIF Steering Group and provide oversight. This group will be able to implement programme-wide management or mitigation measures to ensure LUF project delivery against its stated objectives. / Formal project and funding approval has been obtained via Falkirk Council Executive[21].
6.3b Has a delivery plan been appended to your bid?		Yes / No
6.3c Can you demonstrate ability to begin delivery on the ground in 2021-22?		Yes / No
6.3e Risk Management: Places are asked to set out a detailed risk assessment which sets out (word limit 500 words not including the risk register): / the barriers and level of risk to the delivery of your bid / appropriate and effective arrangements for managing and mitigating these risk / a clear understanding on roles / responsibilities for risk
The barriers and levels of risk associated with the Project are as described in the Risk Register and summarised in section 6.1g of this submission. / The Project Manager – Alistair Dawson (PM) will be responsible for risk management and will continually review the effectiveness of the risk management strategy. / A live risk register will record potential risks which could affect project delivery against programme and budget. It will be regularly reviewed, updated and re-issued through the agreed channels of communication. All risks have been allocated a risk owner. All parties have a shared responsibility to help mitigate risks, by means of good planning, co-ordination, communication and co-operation. When a risk is identified it will be assessed to understand and quantify the chance of the risk occurring and its potential impact on delivery. The risk will be reviewed against its likelihood and the resultant impact. / To ensure clarity on risk status, high risks will be assigned a red status with low risks assigned a green status. Amber status will be assigned to intermediate risks . All risks will be regularly monitored and scored on their impact and probability. The revised priority of risks can then be acted on appropriately. The Council will retain risks which are not transferred or avoided. / Project dashboard reports will be prepared in advance of Programme team meetings. The reports update on project progress, finances, issues, risks and project changes. Contractors will use this to flag up areas of concern or decisions which need to be made at a higher level. / If the construction/study programme is delayed , the PM will update relevant personnel within the governance structure as required. Remedial measures and associated timescales for redressing the issue will be outlined. Where a change is required, the PM (working with the contractors) is to provide an initial cost to establish the viability based on the information available to Falkirk Council Finance. / A standard Falkirk Council change request form will be used, sent to the relevant governance personnel , with the appropriate support outlined. The PM will not act on any change request associated with LUF funding until the Programme Manager has issued instruction. The PM will maintain a change log, detailing all requests for change and their status. This log will be issued by the PM (Alistair Dawson) with the monthly report pack. At the project outset, the PM will agree with the Steering Group a change value limit for authorised sign off. Where the cost of a change exceeds this limit, their authorisation will be required. / The PM will negotiate with senior stakeholders to broker solutions to project issues. They will decide how responsibility for Project Assurance will be met, for instance by delegation to a suitably skilled individual(s) across the Council.
6.3f Has a risk register been appended to your bid?		Yes / No
6.3g Please evidence your track record and past experience of delivering schemes of a similar scale and type (Limit 250 words)
Falkirk Council has extensive experience delivering large-scale infrastructure and development projects, including: / Helix (£43 million) – The Helix park is a large recreational and open area in Falkirk which was the result of transforming over 350 hectares of land. The Helix connects to 16 local communities through an extensive network of paths which stretch over 27km. The Helix includes performance area for large-scale events, facilities for watersports provided by the construction of a large lagoon, and play areas to support a variety of outdoor activities and recreation. / Stadium (£15) – The Falkirk Stadium was delivered as a joint venture project between Falkirk Football Club and Falkirk Council. The stadium opened in 2003 and has become a focus for business and the local community on the eastern edge of Falkirk / Tax Increment Finance (TIF) – the Falkirk TIF programme (Phase 1) commenced in financial year 2013/14 and is providing capital investment to the delivery of several infrastructure projects. For the period ending financial year 2021/22, TIF will have contributing a cumulative £24.9 million to a number of projects, including: / J6 (£2.5m) / J5 (£2.5m) / Westfield (£12.2m) / Icehouse Brae (£4.786m) / Site enabling (£2.942m) / A801 (£0.04m) / The Council has been the delivery body for all of these projects. Furthermore, its TIF programme is acknowledged by Scottish Government to have been the most effective of those operating in Scotland.
6.3h Assurance: We will require Chief Financial Officer confirmation that adequate assurance systems are in place. / For larger transport projects (between £20m - £50m) please provide evidence of an integrated assurance and approval plan. This should include details around planned health checks or gateway reviews. (Limit 250 words)
The Chief Financial Officer confirms that adequate assurance systems are in place / Falkirk Council has established internal governance arrangements for the management of the LUF Programme (see 6.3). Alistair Dawson - Roads, Bridges and Flooding Coordinator at Falkirk Council has the authority to develop the project, including but not limited to managing stakeholders and procuring works for approval prior to submission authorisation by the Steering Group. As noted, the Council has a mechanism for regular progress updates and dialogue on all of the LUF elements between responsible officers and Elected Members. As set out in 6.3, they will be responsible for reporting to the Steering Group on a regular basis and Council if required.
6.4 Monitoring and Evaluation / See technical note Section 4 and Table 1 for further guidance.
6.4a Monitoring and Evaluation Plan: Please set out proportionate plans for M&E which should include (1000 word limit): / Bid level M&E objectives and research questions / Outline of bid level M&E approach / Overview of key metrics for M&E (covering inputs, outputs, outcomes and impacts), informed by bid objectives and Theory of Change. Please complete Tabs E and F on the appended excel spreadsheet / Resourcing and governance arrangements for bid level M&E
Falkirk Council recognises the importance of demonstrating Best Value and progress towards ‘levelling up’. Building on its experience of other TIF projects and the M&E framework for its Investment Zone Deal, the Council has developed an M&E framework to ensure compliance with LUF requirements for performance management and has made allowance for its cost within the Programme Management Costs. / The following targets will be met upon practical completion: / A new two-lane dual carriageway on the A904, from M9 Junction 6 Earlsgate) to Forth Valley College; and on the A9 from the Etna Road (Helix Park) roundabout to the Falkirk Stadium roundabout / Three new roundabouts at Middlefield Road, West Mains Road and serving the proposed further development site known as Falkirk Gateway / An upgraded A9/A904 roundabout, Westfield Roundabout / Improved pedestrian and cycle crossing facilities, by way of an iconic elevated bridge structure / Direct M&E of bridge infrastructure will be supported by Falkirk’s Transport and Planning & Economic Development Teams and Sustrans, via monitoring route usage. A series of counters will be incorporated on each spiral ramp to monitor use from each of the four sites served. Counters will monitor pedestrian and cycle passes regardless of direction. A a beam breaker system is expected to be used on each of the four ramps plus one on the route to West Mains/ Grangemouth. Information will be collected quarterly by Council officers and used to provide feedback on impact. Accident statistics will be monitored for vehicle - pedestrian and vehicle pedal collisions. / The amount of solar energy produced by the bridge will be monitored as will the amount of self-sufficiency of the lighting network associated with the structure. The amount of energy exported to nearby lighting or the LCV Hub will also be monitored. / The teams will also set the following research questions: / Is the infrastructure providing routes to new employment opportunities for local residents? / Is the infrastructure providing new job opportunities for vulnerable residents or groups and supporting Falkirk’s ‘levelling up’ / Quarterly progress reporting on project development and delivery will be provided to CMT, including benefit realisation updates, compliant with recent MHCLG guidance. / Direct M&E of the Falkirk Gateway and Former College site benefits will be monitored through the aforementioned Developer Agreement and the Council’s Planning & Economic Development team respectively. Following provision of access, monthly progress updates will be required to be provided to the Council’s Planning & Economic Development team on progress. This will include but is not limited to: / Number of homes constructed and occupied; / Number of retail & leisure units developed and occupied; / Number of construction jobs supported; / Various community benefits agreed in line with the Councils Community Benefits Strategy (where possible) / The PM will have responsibility for creation and implementation of a Benefits Realisation Strategy to ensure the delivery of the project outcomes for economic development and regeneration. This will utilise the KPIs listed in Tables E & F of Appendix 5. Each KPI will be monitored quarterly. From award through to March 2024, an annual evaluation of the development and construction process, including an assessment of forecast versus outturn project costs, together with reasons for any variance, will be produced for monitoring and evaluation purposes. Following this, a staged monitoring and evaluation plan will take place at each of the following Gateway points: / Gateway 1 (2022) – An initial evaluation, approximately one year into the programme will provide an early indication that the project is operating as planned. / Gateway 2 (2024) – A detailed evaluation, approximately three to four years into the delivery of the entire programme. Analysis will be reported against each of the three project themes: Town Centre & Regeneration, Cultural & Heritage, and Transport. At this stage, we will carry out a more detailed land value uplift assessment, to understand the interventions effect as outlined in the business case. / Gateway 3 (2028) – This crucial stage will consider impacts in the context of data gathered over a longer period and provides a more detailed measurement as to what extent the longer-term objectives have been achieved (i.e. footfall, land value uplift, vacancy rates). This longer timeframe also allows consideration of the impacts of wider initiatives, including the local resident and business sentiment.
[21] Report available at: https://www.falkirk.gov.uk/coins/submissiondocuments.asp?submissionid=18177

PART 7 DECLARATIONS

7.1 Senior Responsible Owner Declaration
As Senior Responsible Owner for Douglas Duff I hereby submit this request for approval to UKG on behalf of Falkirk Council and confirm that I have the necessary authority to do so. / I confirm that Falkirk Council will have all the necessary statutory powers and other relevant consents in place to ensure the planned timescales in the application can be realised.
Name: / Douglas Duff	Signed: / DOUGLAS DUFF / 18/06/2021 / Chief Exec Kenneth Lawrie has also signed off the bid

X04: DECLARATIONS
7.2 Chief Finance Officer Declaration
As Chief Finance Officer for Falkirk Council I declare that the scheme cost estimates quoted in this bid are accurate to the best of my knowledge and that Falkirk Council / has allocated sufficient budget to deliver this scheme on the basis of its proposed funding contribution / accepts responsibility for meeting any costs over and above the UKG contribution requested, including potential cost overruns and the underwriting of any funding contributions expected from third parties / accepts responsibility for meeting any ongoing revenue requirements in relation to the scheme / accepts that no further increase in UKG funding will be considered beyond the maximum contribution requested and that no UKG funding will be provided after 2024-25 / confirm that the authority commits to ensure successful bids will deliver value for money or best value. / confirms that the authority has the necessary governance / assurance arrangements in place and that all legal and other statutory obligations and consents will be adhered to.
Name: Bryan Smail	Signed: / BRYAN SMAIL / 18/06/2021

ECLARATIONS
 0ECLTIONS

7.3 Data Protection
Please note that the The Ministry of Housing, Communities and Local Government (MHCLG) is a data controller for all Levelling Up Fund related personal data collected with the relevant forms submitted to MHCLG, and the control and processing of Personal Data. / The Department, and its contractors where relevant, may process the Personal Data that it collects from you, and use the information provided as part of the application to the Department for funding from the Levelling Up Fund, as well as in accordance with its privacy policies. For the purposes of assessing your bid the Department may need to share your Personal Data with other Government departments and departments in the Devolved Administrations and by submitting this form you are agreeing to your Personal Data being used in this way. / Any information you provide will be kept securely and destroyed within 7 years of the application process completing. / You can find more information about how the Department deals with your data here.

Annex A - Project One Summary (only required for a package bid)
Project 1
A1. Project Name

A2. Strategic Linkage to bid: / Please enter a brief explanation of how this project links strategically to the overall bid. (in no more than 100 words)

A3. Geographical area: / Please provide a short description of the area covered by the bid (in no more than 100 words)

A4. OS Grid Reference
A5. Postcode
A6. For Counties, Greater London Authority and Combined Authorities/Mayoral Combined Authorities, please provide details of the district council or unitary authority where the bid is located (or predominantly located)
A7. Please append a map showing the location (and where applicable the route) of the proposed scheme, existing transport infrastructure and other points of particular interest to the bid e.g. development sites, areas of existing employment, constraints etc.	Yes / No
A8. Project theme Please select the project theme	Transport investment / Regeneration and town centre investment / Cultural investment
A9. Value of capital grant being requested for this project (£):
A10. Value of match funding and sources (£):
A11. Value for Money / This section should set out the full range of impacts – both beneficial and adverse – of the project. Where possible, impacts should be described, quantified and also reported in monetary terms. However there may be some impacts where only a qualitative assessment is possible due to limitations in the available analysis. There should be a clear and detailed explanation of how all impacts reported have been identified, considered and analysed. When deciding what are the most significant impacts to consider, bidders should consider what impacts and outcomes the project is intended to achieve, taking into account the strategic case, but should also consider if there are other possible significant positive or negative impacts, to the economy, people, or environment (Limit 250 word

A12. It will be generally expected that an overall Benefit Cost Ratio and Value for Money Assessment will be reported in applications. If this is not possible, then the application should include a clear explanation of why not.

A13. Where available, please provide the BCR for this project
A14. Does your proposal deliver strong non-monetised benefits? Please set out what these are and evidence them.
A15. Deliverability / Deliverability is one of the key criteria for this Fund and as such any bid should set out any necessary statutory procedures that are needed before it can be constructed.

A16. The Bid – demonstrating investment or ability to begin delivery on the ground in 2021-22 / As stated in the prospectus UKG seeks for the first round of the funding that priority will be given to bids that can demonstrate investment and ability to deliver on the ground in 2021-22
A17. Does this project includes plans for some LUF expenditure in 2021-22?	Yes / No
A18. Could this project be delivered as a standalone project or do it require to be part of the overall bid?	Yes / No
A19. Please provide evidence
A20. Can you demonstrate ability to deliver on the ground in 2021-22.	Yes / No
A21. Please provide evidence
Statutory Powers and Consents
A22. Please list separately each power / consents etc obtained, details of date acquired, challenge period (if applicable) and date of expiry of powers and conditions attached to them. Any key dates should be referenced in your project plan.
A23. Please list separately any outstanding statutory powers / consents etc, including the timetable for obtaining them.

Annex B - Project Two description and funding profile (only required for package bid)
Project 2
B1. Project Name
B2. Strategic Linkage to bid: / Please enter a brief explanation of how this project links strategically to the overall bid. (in no more than 100 words)

B3. Geographical area: / Please provide a short description of the area covered by the bid (in no more than 100 words)

B4. OS Grid Reference
B5.Postcode
B6. For Counties, Greater London Authority and Combined Authorities/Mayoral Combined Authorities, please provide details of the district council or unitary authority where the bid is located (or predominantly located)
B7. Please append a map showing the location (and where applicable the route) of the proposed scheme, existing transport infrastructure and other points of particular interest to the bid e.g. development sites, areas of existing employment, constraints etc.
B8. Project theme Please select the project theme	Transport investment / Regeneration and town centre investment / Cultural investment
B9. Value of capital grant being requested for this project (£):
B10. Value of match funding and sources (£):
B11. Value for Money / This section should set out the full range of impacts – both beneficial and adverse – of the project. Where possible, impacts should be described, quantified and also reported in monetary terms. However there may be some impacts where only a qualitative assessment is possible due to limitations in the available analysis. There should be a clear and detailed explanation of how all impacts reported have been identified, considered and analysed. When deciding what are the most significant impacts to consider, bidders should consider what impacts and outcomes the project is intended to achieve, taking into account the strategic case, but should also consider if there are other possible significant positive or negative impacts, to the economy, people, or environment

B12. It will be generally expected that an overall Benefit Cost Ratio and Value for Money Assessment will be reported in applications. If this is not possible, then the application should include a clear explanation of why not.

B13. Where available, please provide the BCR for this project
B14. Does your proposal deliver strong non-monetised benefits? Please set out what these are and evidence them.
B15. Deliverability / Deliverability is one of the key criteria for this Fund and as such any bid should set out any necessary statutory procedures that are needed before it can be constructed.

B16. The Bid – demonstrating investment or ability to begin delivery on the ground in 2021-22 / As stated in the prospectus UKG seeks for the first round of the funding that priority will be given to bids that can demonstrate investment and ability to deliver on the ground in 2021-22

B17. Does this project includes plans for some LUF expenditure in 2021-22?	Yes / No
B18. Could this project be delivered as a standalone project or do it require to be part of the overall bid?	Yes / No
B19. Please provide evidence
B20. Can you demonstrate ability to deliver on the ground in 2021-22.	Yes / No
B21. Please provide evidence
Statutory Powers and Consents
B22. Please list separately each power / consents etc obtained, details of date acquired, challenge period (if applicable) and date of expiry of powers and conditions attached to them. Any key dates should be referenced in your project plan.
B23. Please list separately any outstanding statutory powers / consents etc, including the timetable for obtaining them.

Annex C – Project Three- description and funding profile (only required for package bid)
Project 3
C1. Project Name
C2. Strategic Linkage to bid: / Please enter a brief explanation of how this project links strategically to the overall bid. (in no more than 100 words)

C3. Geographical area: / Please provide a short description of the area covered by the bid (in no more than 100 words)

C4. OS Grid Reference
C5. Postcode
C6. For Counties, Greater London Authority and Combined Authorities/Mayoral Combined Authorities, please provide details of the district council or unitary authority where the bid is located (or predominantly located)
C7. Please append a map showing the location (and where applicable the route) of the proposed scheme, existing transport infrastructure and other points of particular interest to the bid e.g. development sites, areas of existing employment, constraints etc.
C8. Project theme Please select the project theme	Transport investment / Regeneration and town centre investment / Cultural investment
C9. Value of capital grant being requested for this project (£):
C10. Value of match funding and sources (£):
C11. Value for Money / This section should set out the full range of impacts – both beneficial and adverse – of the project. Where possible, impacts should be described, quantified and also reported in monetary terms. However there may be some impacts where only a qualitative assessment is possible due to limitations in the available analysis. There should be a clear and detailed explanation of how all impacts reported have been identified, considered and analysed. When deciding what are the most significant impacts to consider, bidders should consider what impacts and outcomes the project is intended to achieve, taking into account the strategic case, but should also consider if there are other possible significant positive or negative impacts, to the economy, people, or environment

C12. It will be generally expected that an overall Benefit Cost Ratio and Value for Money Assessment will be reported in applications. If this is not possible, then the application should include a clear explanation of why not.

C13. Where available, please provide the BCR for this project
C14. Does your proposal deliver strong non-monetised benefits? Please set out what these are and evidence them.
C15. Deliverability / Deliverability is one of the key criteria for this Fund and as such any bid should set out any necessary statutory procedures that are needed before it can be constructed.

C16. The Bid – demonstrating investment or ability to begin delivery on the ground in 2021-22 / As stated in the prospectus UKG seeks for the first round of the funding that priority will be given to bids that can demonstrate investment and ability to deliver on the ground in 2021-22
C17. Does this project includes plans for some LUF expenditure in 2021-22?	Yes / No
C18. Could this project be delivered as a standalone project or do it require to be part of the overall bid?	Yes / No
C19. Please provide evidence
C20. Can you demonstrate ability to deliver on the ground in 2021-22.	Yes / No
C21. Please provide evidence
Statutory Powers and Consents
C22. Please list separately each power / consents etc obtained, details of date acquired, challenge period (if applicable) and date of expiry of powers and conditions attached to them. Any key dates should be referenced in your project plan.
C23. Please list separately any outstanding statutory powers / consents etc, including the timetable for obtaining them.

ANNEX D - Check List Great Britain Local Authorities

Questions	Y/N	Comments
4.1a Member of Parliament support
MPs have the option of providing formal written support for one bid which they see as a priority. Have you appended a letter from the MP to support this case?	Y	Appendix 8
Part 4.2 Stakeholder Engagement and Support
Where the bidding local authority does not have responsibility for the delivery of projects, have you appended a letter from the responsible authority or body confirming their support?	N/A
Part 4.3 The Case for Investment
For Transport Bids: Have you provided an Option Assessment Report (OAR)	Y	While not defined as Falkirk’s ‘major transport bid’ please see / Appendix 6
Part 6.1 Financial
Have you appended copies of confirmed match funding?	Yes	Falkirk Council confirms its co-funding. See Appendix 9 for LCTT confirmation.
The UKG may accept the provision of land from third parties as part of the local contribution towards scheme costs. Please provide evidence in the form of a letter from an independent valuer to verify the true market value of the land. / Have you appended a letter to support this case?	N/A
Part 6.3 Management
Has a delivery plan been appended to your bid?	Yes	Appendix 7
Has a letter relating to land acquisition been appended?	N/A
Have you attached a copy of your Risk Register?	Yes
Annex A-C - Project description Summary (only required for package bid)
Have you appended a map showing the location (and where applicable the route) of the proposed scheme, existing transport infrastructure and other points of particular interest to the bid e.g. development sites, areas of existing employment, constraints etc.

Annex E Checklist for Northern Ireland Bidding Entities
Questions	Y/N	Comments
Part 1 Gateway Criteria
You have attached two years of audited accounts
You have provided evidence of the delivery team having experience of delivering two capital projects of similar size and in the last five years
Part 4.2 Stakeholder Engagement and Support
For transport bids, have you appended a letter of support from the relevant district council
Part 6.1 Financial
Have you appended copies of confirmed match funding
The UKG may accept the provision of land from third parties as part of the local contribution towards scheme costs. Please provide evidence in the form of a letter from an independent valuer to verify the true market value of the land.
Part 6.3 Management
Has a delivery plan been appended to your bid?
Has a letter relating to land acquisition been appended?
Have you attached a copy of your Risk Register?
Annex A-C - Project description Summary (only required for package bid)
Have you appended a map showing the location (and where applicable the route) of the proposed scheme, existing transport infrastructure and other points of particular interest to the bid e.g. development sites, areas of existing employment, constraints etc.